## Employee_data
Employee Name | Employee Email ID | Team | Sub Team
Mikko Virtanen | mikko.virtanen@nokia.com | Core | Backend
Aditya Patel | aditya.patel@nokia.com | Core | Backend
Elena Petrova | elena.petrova@nokia.com | Core | Frontend
Matti Korhonen | matti.korhonen@nokia.com | Platform | DevOps
Sneha Rao | sneha.rao@nokia.com | Platform | QA
Lukas Schmidt | lukas.schmidt@nokia.com | Platform | QA
Kaisa Laine | kaisa.laine@nokia.com | Management | Strategy
Rajesh Nair | rajesh.nair@nokia.com | Management | PMO
Antti Koskinen | antti.koskinen@nokia.com | Network | Infrastructure
Sandeep Sharma | sandeep.sharma@nokia.com | Network | Infrastructure
Sofia Fischer | sofia.fischer@nokia.com | Network | Cloud
Jan Virtanen | jan.virtanen@nokia.com | Network | Cloud
Ville Nieminen | ville.nieminen@nokia.com | Security | AppSec
Jyoti Mishra | jyoti.mishra@nokia.com | Security | AppSec
Markus Meyer | markus.meyer@nokia.com | Security | Compliance

## Sprint_Date
FB | Start | End
FB-23 | 2025-04-14 | 2025-04-25
FB-24 | 2025-04-28 | 2025-05-09
FB-25 | 2025-05-12 | 2025-05-23
FB-26 | 2025-05-26 | 2025-06-06
FB-27 | 2025-06-09 | 2025-06-20
FB-28 | 2025-06-23 | 2025-07-04

## Sprint_Planning
FB | Employee Name | Feature ID | Feature Description | Activity Type | Activity Description | Activity Status | Est Effort | Spent Effort
FB-23 | Antti Koskinen | F-106 | API Gateway Refactor | Design | Design gateway request caching topology | In Progress | 6 | 2.2
FB-23 | Markus Meyer | F-107 | Cloud Native Migration | Testing | Perform disaster recovery simulation audits | Done | 12 | 11.4
FB-23 | Lukas Schmidt | F-101 | 5G RAN Controller | Testing | Validate latency bounds under heavy traffic load | Done | 14 | 13.7
FB-23 | Ville Nieminen | F-101 | 5G RAN Controller | Testing | Validate latency bounds under heavy traffic load | Done | 13 | 11.1
FB-23 | Mikko Virtanen | F-101 | 5G RAN Controller | Design | Create packet prioritization flow architecture | Done | 9 | 9.3
FB-23 | Elena Petrova | F-105 | SLA Monitoring Dashboard | Design | Draw mockups for target metrics and SLA breaches panel | Done | 16 | 13
FB-23 | Sandeep Sharma | F-105 | SLA Monitoring Dashboard | Development | Implement monthly uptime percentage math calculator | Blocked | 11 | 2.9
FB-23 | Jan Virtanen | F-104 | Alarm Management UI | Design | Refine alert color codes and grouping layouts | Done | 13 | 13.1
FB-23 | Sneha Rao | F-106 | API Gateway Refactor | DevOps | Set up service mesh configurations for gateway routing | Done | 9 | 10.4
FB-24 | Lukas Schmidt | F-106 | API Gateway Refactor | Testing | Load test API Gateway against 50k RPS | Done | 11 | 10.5
FB-24 | Antti Koskinen | F-102 | Network Slice Manager | Design | Map resource reservation strategy for multi-tenancy | Done | 10 | 9.6
FB-24 | Mikko Virtanen | F-106 | API Gateway Refactor | Development | Implement token bucket rate limiter in Go | Done | 6 | 6.2
FB-24 | Sofia Fischer | F-106 | API Gateway Refactor | DevOps | Set up service mesh configurations for gateway routing | Done | 8 | 9.6
FB-24 | Elena Petrova | F-107 | Cloud Native Migration | Testing | Perform disaster recovery simulation audits | In Progress | 11 | 6.5
FB-24 | Aditya Patel | F-101 | 5G RAN Controller | Testing | Validate latency bounds under heavy traffic load | Done | 7 | 8.4
FB-24 | Rajesh Nair | F-104 | Alarm Management UI | Documentation | Draft alarm manager user handbook | Done | 5 | 4.3
FB-24 | Sneha Rao | F-109 | Performance Analytics Engine | Testing | Write integration test suite for KPI aggregators | Done | 9 | 9.9
FB-24 | Sandeep Sharma | F-101 | 5G RAN Controller | DevOps | Set up low-latency kernel configurations on testing nodes | Blocked | 5 | 1
FB-25 | Mikko Virtanen | F-101 | 5G RAN Controller | Testing | Validate latency bounds under heavy traffic load | Blocked | 9 | 1
FB-25 | Aditya Patel | F-107 | Cloud Native Migration | Development | Migrate stateful file persistence to S3 storage API | Done | 8 | 7.2
FB-25 | Sandeep Sharma | F-108 | Security Audit Module | DevOps | Add Static Application Security Testing (SAST) to CI | In Progress | 15 | 7.9
FB-25 | Jyoti Mishra | F-107 | Cloud Native Migration | Documentation | Write Kubernetes migration roadmap guidelines | Done | 3 | 3.2
FB-25 | Antti Koskinen | F-103 | OSS Integration Layer | Development | Build Kafka message consumers for node notifications | Done | 4 | 4.3
FB-25 | Lukas Schmidt | F-103 | OSS Integration Layer | Testing | Validate data integrity across event correlation pipeline | Done | 13 | 11.6
FB-25 | Jan Virtanen | F-102 | Network Slice Manager | Design | Map resource reservation strategy for multi-tenancy | Done | 3 | 3.3
FB-25 | Sofia Fischer | F-107 | Cloud Native Migration | Design | Architect stateless deployment patterns for Core services | Done | 7 | 6
FB-25 | Matti Korhonen | F-105 | SLA Monitoring Dashboard | Testing | QA test warning alert triggers on SLA violation mocks | Done | 8 | 6.8
FB-26 | Jan Virtanen | F-107 | Cloud Native Migration | DevOps | Create AWS cloud formation scripts for core stack | Done | 5 | 5
FB-26 | Elena Petrova | F-109 | Performance Analytics Engine | Testing | Write integration test suite for KPI aggregators | Done | 11 | 9.4
FB-26 | Rajesh Nair | F-109 | Performance Analytics Engine | Analysis | Investigate CPU utilization bottlenecks on aggregators | Blocked | 11 | 2.7
FB-26 | Sofia Fischer | F-104 | Alarm Management UI | Design | Refine alert color codes and grouping layouts | In Progress | 8 | 2.7
FB-26 | Mikko Virtanen | F-109 | Performance Analytics Engine | Development | Optimize ClickHouse time-series metric aggregations | In Progress | 6 | 3.9
FB-26 | Lukas Schmidt | F-105 | SLA Monitoring Dashboard | Testing | QA test warning alert triggers on SLA violation mocks | To Do | 3 | 0
FB-26 | Ville Nieminen | F-109 | Performance Analytics Engine | Testing | Write integration test suite for KPI aggregators | To Do | 6 | 0
FB-26 | Antti Koskinen | F-109 | Performance Analytics Engine | DevOps | Configure DB sharding and replication properties | Done | 15 | 18
FB-26 | Jyoti Mishra | F-101 | 5G RAN Controller | Testing | Validate latency bounds under heavy traffic load | In Progress | 7 | 3.7
FB-27 | Ville Nieminen | F-107 | Cloud Native Migration | Testing | Perform disaster recovery simulation audits | To Do | 16 | 0
FB-27 | Rajesh Nair | F-109 | Performance Analytics Engine | Analysis | Investigate CPU utilization bottlenecks on aggregators | To Do | 12 | 0
FB-27 | Jyoti Mishra | F-101 | 5G RAN Controller | Analysis | Compare throughput stats against competitor platforms | In Progress | 12 | 8.3
FB-27 | Jan Virtanen | F-106 | API Gateway Refactor | Design | Design gateway request caching topology | In Progress | 12 | 4.2
FB-27 | Kaisa Laine | F-101 | 5G RAN Controller | Documentation | Draft RAN connection configuration manuals | To Do | 16 | 0
FB-27 | Mikko Virtanen | F-108 | Security Audit Module | Design | Map secure role-based access control (RBAC) scopes | To Do | 13 | 0
FB-27 | Sneha Rao | F-107 | Cloud Native Migration | Testing | Perform disaster recovery simulation audits | To Do | 8 | 0
FB-27 | Markus Meyer | F-104 | Alarm Management UI | Documentation | Draft alarm manager user handbook | To Do | 8 | 0
FB-27 | Elena Petrova | F-104 | Alarm Management UI | Development | Build virtualized scroll list view for 10k alerts | To Do | 9 | 0
FB-28 | Lukas Schmidt | F-101 | 5G RAN Controller | Analysis | Compare throughput stats against competitor platforms | In Progress | 9 | 3.8
FB-28 | Aditya Patel | F-108 | Security Audit Module | Testing | Conduct automated pen testing on login endpoints | In Progress | 15 | 10.3
FB-28 | Sneha Rao | F-106 | API Gateway Refactor | DevOps | Set up service mesh configurations for gateway routing | To Do | 13 | 0
FB-28 | Jyoti Mishra | F-108 | Security Audit Module | Documentation | Update compliance and audit readiness policies | To Do | 16 | 0
FB-28 | Ville Nieminen | F-108 | Security Audit Module | Analysis | Assess vulnerability reports from scanner runs | To Do | 12 | 0
FB-28 | Antti Koskinen | F-106 | API Gateway Refactor | DevOps | Set up service mesh configurations for gateway routing | To Do | 14 | 0
FB-28 | Markus Meyer | F-108 | Security Audit Module | Analysis | Assess vulnerability reports from scanner runs | To Do | 12 | 0
FB-28 | Mikko Virtanen | F-105 | SLA Monitoring Dashboard | Design | Draw mockups for target metrics and SLA breaches panel | To Do | 3 | 0
FB-28 | Matti Korhonen | F-103 | OSS Integration Layer | DevOps | Deploy dedicated Kafka cluster nodes via Helm charts | To Do | 3 | 0